PI/PO NARRATIVE – SR-269

INTRODUCTION - Slide 1:

The following is the online public involvement presentation for the Alabama Department of Transportation’s project BR-0269(511).

WELCOME - Slide 2:

Welcome and thank you for participating in the online public involvement for the proposed bridge replacement on AL-269 (Birmingport Road) in Jefferson County, Alabama.  We want to provide an opportunity for you to review and comment on the proposed project. Your input is crucial to the advancement of this project. The information provided within this presentation is preliminary and subject to change.

PROJECT LOCATION - Slide 3:

The project is located on AL-269 (Birmingport Road) a rural major collector in west Jefferson County.  The bridge to be replaced crosses over the Locust Fork of the Warrior River.  Development within the project corridor is primarily industrial with some residential facilities.  The terrain is relatively flat. AL-269 provides direct access to an active port facility.

PURPOSE AND NEED - Slide 4:

The existing bridge over Locust Fork has been in service since the mid-1960’s. The bridge is approximately 770’ long and 28’ wide.  The existing bridge has 2 – 12’ lanes and 2’ shoulders.

The current structure is deteriorating and is too narrow to accommodate current vehicles, meet AASHTO standards or the Coast Guard requirements.

A new bridge is proposed to preserve a safer and more efficient transportation system.

SCOPE OF WORK - Slide 5:

The proposed bridge will be constructed east of the existing and span the Locust Fork. No piers would be placed in the river.   The new bridge is anticipated to be approximately 940 ft long and 44 ft wide.  The width would accommodate 2 – 12 ft lanes and 2 – 10’ shoulders.

To meet current Coast Guard clearance requirements, the new bridge will be raised approximately 10 ft.

PROJECT SCHEDULE - Slide 6:

Additional right-of-way and utility relocations will be required for the bridge replacement.  The acquisition process of the required right of way is projected to begin late 2026.  The utility relocations are scheduled for early 2027.  Construction will tentatively begin Fall 2027.

The bridge over the Locust Fork of the Warrior River will be closed. The roadway will be accessible during construction for local traffic only. Intermittent lane closures are to be expected.

A detour for thru traffic is planned for this project.

Construction is anticipated to take between 18 – 24 months.

PROPOSED DETOUR – Slide 7:

As a result of the bridge over the Locust Fork of the Warrior River being closed, traffic for AL-269(Birmingport Road) will be detoured onto Alliance Short Creek Road and Alliance Road.

- For Northbound traffic – The detour begins at the intersection of AL-269 and Alliance Short Creek Road.  The detour will continue onto Alliance Road and proceed north to

AL-269.

- For Southbound traffic – The detour begins at the intersection of AL-269 and Alliance Road.  The detour will continue south on Alliance Road onto Alliance Short Creek Road and proceed east to AL-269.

PROVIDE YOUR COMMENTS - Slide 8:

There will not be an in-person public involvement meeting for this project.  You can make inquiries and/or provide comments regarding this project online, by voice mail or US mail as noted.  Please provide your comments by July 10, 2026.

CONTACT INFORMATION – Slide 9:

If you should have any questions or require additional information, please contact our Communications and Public Relations Coordinator, Jon Paepcke.

Thank you for your interest and participation